## AI Security Backlog
ID | Work Item Type | Title | Security Framework | Priority | Risk Level | Area | State | Description | Acceptance Criteria | Effort | File Reference
1 | Feature | Implement Prompt Injection Defense | AI-Specific Security | 1 | Critical | AI Agent | New | No prompt injection defense on user input. req.message passed directly to GPT with no sanitization, canary tokens, or input/output classifiers. Violates OWASP LLM01 and Microsoft CAF Agent Security Requirement #5. | Azure AI Content Safety Prompt Shields integrated. All user inputs scanned before LLM submission. Injection attempts blocked and logged. Canary token detection active. | L | api.py L357
2 | Feature | Implement Model Output Validation Pipeline | AI-Specific Security | 1 | High | AI Agent | New | LLM responses streamed directly to client via SSE with no post-processing for harmful content, PII leakage, or injection payloads. Violates OWASP LLM02. | Output validation layer filters PII, harmful content, and injection payloads before client delivery. Content Safety text analysis on all outputs. Blocked content logged. | L | api.py L601-L650
3 | Feature | Integrate Azure AI Content Safety Service | AI-Specific Security | 1 | High | Infra | New | Platform assesses OTHER tenants for content safety gaps but has no Content Safety integration on its own OpenAI calls. No Prompt Shields, no Groundedness Detection, no Protected Material Detection, no Task Adherence. | Content Safety resource provisioned. Prompt Shields on all inputs. Groundedness Detection on assessment outputs. Task Adherence monitors tool use. Protected Material Detection on reports. | L | api.py L160-L170
4 | User Story | Sanitize tool results before LLM injection | AI-Specific Security | 2 | High | AI Agent | New | As a security engineer, tool output (which may contain attacker-controlled data like Azure resource names, tags, descriptions) is injected as role:tool messages without sanitization. Indirect prompt injection vector. | Tool results sanitized: HTML entities escaped, length truncated, special chars stripped. Injection test suite with adversarial Azure resource names passes. | M | api.py L650-L660
5 | User Story | Add grounding verification for LLM outputs | AI-Specific Security | 2 | Medium | AI Agent | New | As a QA engineer, system prompt instructs against hallucination but no programmatic check verifies LLM output is grounded in tool results. Cloud Explorer mode especially vulnerable. | Groundedness Detection API validates assessment recommendations are grounded in evidence. Ungrounded content flagged with confidence score <0.7. | M | System design
6 | Feature | Implement JWT Signature Verification | Zero Trust | 1 | Critical | AI Agent | New | JWT decoded without signature verification. _extract_exp uses base64 only. Comment says "real validation happens when Azure APIs consume the token" but this means the app trusts ANY token with valid base64 structure. Violates Zero Trust "verify explicitly". | PyJWT decode with verify=True. JWKS endpoint cached for token validation. Signature, issuer, audience, expiry all verified. Invalid tokens rejected with 401. | M | core/auth.py L62-L75
7 | User Story | Fix token expiry enforcement | Zero Trust | 1 | High | AI Agent | New | As a security engineer, UserTokenCredential only warns if token expires in <120s but still returns the near-expired/expired token. Downstream requests fail silently with 401. | Exception raised when token <120s from expiry. Client receives 401 with refresh instruction. Token refresh attempted automatically before expiry. | S | core/auth.py L117-L122
8 | Feature | Move OAuth tokens to Authorization header | Zero Trust | 1 | High | AI Agent | New | OAuth tokens (graph_token, arm_token) passed in POST body JSON to /chat endpoint. Tokens logged at DEBUG level, stored in conversation memory, and passed to LLM context. Should use Authorization header with token scrubbing. | Tokens via Authorization header (Bearer scheme). POST body contains no tokens. All log pipelines scrub token patterns. Memory cleared post-request. | L | api.py L270-L273
9 | User Story | Implement distributed rate limiter | Zero Trust | 2 | Medium | AI Agent | New | As a platform engineer, _rate_buckets is process-local dict. Container App scales 0-3 replicas so each replica has independent rate limit counters. Attacker can multiply effective rate by number of replicas. | Redis-backed rate limiter shared across replicas. Redis failover degrades to local gracefully. Rate limit headers (X-RateLimit-*) returned to clients. | M | api.py L208-L236
10 | Feature | Add WAF and VNET Integration | Zero Trust | 1 | High | Infra | New | Container App ingress is external with no VNET integration, no WAF, direct public endpoint. No micro-segmentation. Violates Zero Trust "assume breach" and FedRAMP SC-7 Boundary Protection. | Azure Front Door with WAF (OWASP 3.2 ruleset). Container App in VNET with internal ingress. NSG restricts to Front Door only. DDoS Standard protection. | XL | deploy.ps1 L381
11 | User Story | Implement session binding for tokens | Zero Trust | 3 | Medium | AI Agent | New | As a security engineer, tokens not bound to session/device. Any party with the token can replay from different IP/device. No session fingerprinting. | Session bound to IP + User-Agent hash. Token replay from different fingerprint requires re-authentication. Session state tracked server-side. | M | System design
12 | Feature | Enable Microsoft Defender for AI Services | Defender for AI | 1 | High | Infra | New | Defender for Cloud not enabled on any resource. No Defender for AI Services plan. No AI threat detection (prompt injection, jailbreak, data leakage, credential theft alerts). Microsoft CAF Agent Security Requirement #2. | Defender for Cloud enabled. Defender for AI Services plan active on Azure OpenAI resource. Threat alerts routed to SOC. 30-day free trial activated. | M | deploy.ps1
13 | User Story | Enable AI-specific threat detection alerts | Defender for AI | 1 | High | Infra | New | As an SRE, no AI-specific threat detection. No Prompt Shields on own endpoint for self-monitoring. No Azure AI Content Safety resource provisioned for the platform itself. | Defender for AI alerts configured: prompt injection, jailbreak, data leakage, credential theft. Alerts integrated with Defender XDR. Severity-based routing. | M | Infra & app code
14 | User Story | Implement token usage anomaly detection | Defender for AI | 2 | Medium | AI Agent | New | As an SRE, token counts tracked per-request but no alerting on usage spikes/anomalies. Single user could exhaust 30K TPM without detection. | Azure Monitor alert on token usage >80% of TPM limit. Anomaly detection for per-user usage patterns. Cost attribution alerts per department. | M | api.py L580-L585
15 | User Story | Implement structured security event logging | Defender for AI | 2 | Medium | AI Agent | New | As an SRE, auth failures, rate limit hits, tool execution errors logged as generic messages, not structured security events. Cannot query security events in Log Analytics. | Dedicated security event category. Structured JSON: event_type, severity, user_id, action, outcome, details. KQL queries for SOC dashboards. | M | core/logger.py
16 | Feature | LLM01: Comprehensive Prompt Injection Defense | OWASP LLM Top 10 | 1 | Critical | AI Agent | New | CRITICAL: User input passed directly to messages array with no sanitization. Tool results (containing attacker-controlled Azure resource names) fed back to LLM. Both direct and indirect prompt injection vectors open. | Input sanitization layer. Prompt Shields on all inputs. Tool result sandboxing. Canary token detection. Red team test suite with 50+ injection patterns all blocked. | L | api.py L357
17 | Feature | LLM02: Secure Output Handling | OWASP LLM Top 10 | 1 | High | AI Agent | New | LLM output streamed directly as SSE to browser. Reports use custom esc() function that manually escapes & < > " but misses single quote. No markupsafe usage. No Jinja2 autoescape. | Jinja2 autoescape=True globally. Replace custom esc with markupsafe.escape. SSE output sanitized. XSS test suite with 100+ payloads passes. | M | shared_theme.py L23-L25
18 | User Story | LLM04: Model Denial of Service protection | OWASP LLM Top 10 | 2 | Medium | AI Agent | New | As a platform engineer, rate limiter exists but in-memory only. 900s OpenAI timeout. No per-user token budget. max_rounds=10 limits tool iterations but no global cost cap. | Per-user token budget (10K tokens/hour default). Global cost cap per assessment. Distributed rate limiter. OpenAI timeout reduced to 120s. | M | api.py L208-L236
19 | User Story | LLM05: Supply chain hardening | OWASP LLM Top 10 | 2 | Medium | DevOps | New | As a security engineer, beta/RC SDKs in production (agent-framework-azure-ai==1.0.0rc3, azure-ai-agentserver-agentframework==1.0.0b16). No Dependabot. No SBOM generation. Trivy scans but no enforcement. | Dependabot enabled. SBOM generated per release. Trivy blocks Critical/High. Beta SDKs tracked for GA migration. Weekly dependency review. | M | requirements.txt L2-L4
20 | Feature | LLM06: Prevent Sensitive Information Disclosure | OWASP LLM Top 10 | 1 | High | AI Agent | New | Tokens in POST body, JWT decoded in multiple places, token claims logged if DEBUG enabled. Assessment results may contain secrets from evidence. No PII masking in logs. | Token scrubbing in all log pipelines. PII masking regex (emails, IPs, keys, connection strings). Evidence sanitization before storage. No secrets in LLM context. | L | api.py, core/auth.py
21 | User Story | LLM07: Validate tool arguments from LLM | OWASP LLM Top 10 | 2 | Medium | AI Agent | New | As a security engineer, tool arguments passed from LLM directly to Python functions without validation. domains parameter not validated against allowlist. | Pydantic strict validation on all tool arguments. domains validated against known Azure resource types. Argument length limits. Invalid args rejected with structured error. | M | Tool definitions
22 | User Story | LLM08: Reduce excessive agency | OWASP LLM Top 10 | 2 | Medium | AI Agent | New | As a security engineer, 14 tools available including search_tenant which executes arbitrary Resource Graph queries. max_rounds=10, page-level isolation exists but tool capabilities broad. | Resource Graph queries limited to read-only with allowlisted query patterns. Tool capabilities documented with risk classification. Human-in-the-loop for high-risk operations. | M | api.py tool definitions
23 | User Story | LLM06: Mask PII in assessment evidence | OWASP LLM Top 10 | 1 | High | AI Agent | New | As a compliance officer, assessment evidence may contain passwords, API keys, connection strings found during tenant scanning. Stored unmasked. Exported as-is in reports. | Evidence sanitization layer. Regex detection for 15+ secret patterns. Masked before storage. Reports show [REDACTED]. Original available only with elevated RBAC. | L | Evidence collectors
24 | Bug | Fix custom esc missing single-quote escape | OWASP LLM Top 10 | 1 | High | AI Agent | New | Custom esc function in shared_theme.py only escapes & < > double-quote but misses single quote. XSS via single-quote injection in attribute contexts. | Replace custom esc with markupsafe.escape which handles all 5 HTML special chars. Unit test with single-quote XSS payload passes. | S | shared_theme.py L23-L25
25 | Bug | Fix CSV injection in Excel exports | OWASP LLM Top 10 | 2 | Medium | AI Agent | New | Excel/CSV exports via openpyxl do not escape formula characters (=, +, -, @, tab, return). Malicious Azure resource names could execute formulas. | All cell values prefixed with single-quote if starting with formula chars. Test with =CMD payload verified safe. | S | Report generators
26 | Feature | NIST AI RMF GOVERN: AI Governance Documentation | NIST AI RMF | 2 | Medium | Architecture | New | No AI governance documentation exists. No Responsible AI Impact Assessment. No model risk register. No AI incident response plan. NIST AI RMF GOVERN function at Level 1 (Ad hoc). | AI Governance Policy document. RAI Impact Assessment completed. Model risk register with quarterly review. AI incident response plan with runbook. | L | Documentation
27 | User Story | NIST AI RMF MAP: Document AI system boundaries | NIST AI RMF | 2 | Medium | Architecture | New | As a compliance officer, no formal AI use case documentation, no stakeholder mapping, no bias assessment for security recommendations, no documentation of AI system boundaries. | AI use case inventory. Stakeholder RACI matrix. System boundary documentation (what AI decides vs what humans decide). Data flow diagrams. | M | Documentation
28 | User Story | NIST AI RMF MEASURE: Implement accuracy benchmarks | NIST AI RMF | 2 | Medium | AI Agent | New | As a QA engineer, determinism tests exist (5 files) but no systematic accuracy measurement, no ground-truth benchmarks, no hallucination rate tracking, no fairness metrics. | Ground-truth benchmark suite (50+ known-good assessments). Hallucination rate <5%. Accuracy tracked per model version. Fairness metrics across resource types. | L | tests/
29 | User Story | NIST AI RMF MANAGE: Model lifecycle management | NIST AI RMF | 2 | Medium | AI Agent | New | As a platform engineer, model fallback exists (gpt-4.1 to gpt-5.1) but no model drift monitoring, no A/B testing, no automated rollback triggers, no human-in-the-loop for critical decisions. | Model drift detection via weekly benchmark runs. A/B testing framework for model upgrades. Automated rollback on accuracy drop >10%. HITL for critical security recommendations. | L | api.py L596-L610
30 | Feature | RAI: Privacy and Security Controls | Responsible AI | 1 | High | AI Agent | New | Privacy/Security principle WEAK. Tokens in POST body, localStorage MSAL cache, no PII masking, assessment evidence may contain credentials, no GDPR erasure support. Microsoft RAI Privacy and Security principle violated. | GDPR erasure endpoint. PII masking pipeline. Tokens in secure headers. sessionStorage for MSAL. Evidence sanitization. Privacy impact assessment documented. | XL | Multiple files
31 | Feature | RAI: Accountability and Audit Trail | Responsible AI | 1 | High | AI Agent | New | Accountability principle WEAK. No audit logging of who ran which assessment. No user accountability trail. No model decision logging. Cannot trace recommendation to evidence to user. | Full audit trail: user to assessment to evidence to finding to recommendation. Queryable in Log Analytics. Tamper-proof (append-only). 7-year retention. | L | System design
32 | User Story | RAI: Implement transparency disclosures | Responsible AI | 2 | Medium | Webapp | New | As a user, no explicit "I am AI" disclosure. Tool-calling SSE events visible but no explanation of AI limitations or confidence levels in recommendations. | AI disclosure banner on all assessment pages. Confidence scores on recommendations. Explanation of AI limitations. Link to RAI documentation. | M | webapp/*.html
33 | User Story | RAI: Implement fairness testing | Responsible AI | 2 | Medium | AI Agent | New | As a compliance officer, no bias testing on security recommendations. AI may disproportionately flag resources based on naming patterns. No fairness metrics. | Bias testing across resource naming patterns, regions, subscription types. Fairness metrics tracked per model version. Quarterly review. | M | Tests
34 | User Story | RAI: Add user feedback mechanism | Responsible AI | 3 | Low | Webapp | New | As a user, no way to challenge or report incorrect AI-generated decisions. No feedback loop for improving AI recommendations. | Thumbs up/down on each recommendation. Free-text feedback. Feedback reviewed weekly. Model fine-tuning informed by feedback trends. | M | webapp/*.html
35 | User Story | RAI: Implement explainability for recommendations | Responsible AI | 3 | Low | AI Agent | New | As a user, AI recommendations have no confidence scores and no explanation of reasoning. Cannot understand why a specific finding was flagged. | Confidence score (0-1) on each finding. Evidence chain visible. Reasoning explanation in natural language. "Why this recommendation" expandable section. | M | api.py, reports
36 | Feature | Migrate from beta/RC SDK dependencies | Supply Chain | 1 | High | AI Agent | New | agent-framework-azure-ai==1.0.0rc3 and azure-ai-agentserver-agentframework==1.0.0b16 are pre-release SDKs with potential breaking changes and unfixed vulnerabilities. Production dependency on beta code. | Track GA release dates. Migration plan for each SDK. Automated compatibility test. Pin to GA within 30 days of release. | M | requirements.txt L2-L4
37 | User Story | Add base image provenance verification | Supply Chain | 2 | Medium | DevOps | New | As a security engineer, custom base image FROM esiqnewacr.azurecr.io/python:3.12-slim with no provenance verification or image signing. No way to verify image integrity. | Base image signed with cosign. Provenance attestation. Verify signature in CI before build. Pin to digest not tag. | M | Dockerfile L1
38 | User Story | Enable Dependabot / Renovate for dependencies | Supply Chain | 2 | Medium | DevOps | New | As a security engineer, dependency updates are manual only. No automated scanning for vulnerable transitive dependencies. | Dependabot enabled. Weekly scan. Auto-PR for Critical/High CVEs. Dashboard in Security tab. SLA: Critical=24h, High=7d. | S | Repository config
39 | User Story | Generate SBOM per release | Supply Chain | 2 | Medium | DevOps | New | As a compliance officer, Trivy scans for vulns but no Software Bill of Materials produced or stored. Cannot provide supply chain inventory. | SBOM (SPDX or CycloneDX) generated in CI. Stored with release artifacts. Includes all pip packages and OS packages. | S | .github/workflows/deploy.yml
40 | User Story | Implement container image signing | Supply Chain | 3 | Low | DevOps | New | As a security engineer, built images pushed to ACR without cosign/notary signatures. No way to verify image was built by trusted CI pipeline. | cosign sign in CI after build. ACR content trust enabled. Deploy rejects unsigned images. Key rotation plan. | M | CI pipeline
41 | User Story | Add post-deploy smoke tests | Supply Chain | 3 | Low | DevOps | New | As a DevOps engineer, deployment just updates image and prints FQDN. No health check validation post-deployment. Broken deploys not detected until user reports. | Smoke test: /health returns 200, /chat auth works, static assets load. Blocks promotion on failure. Alert on smoke test failure. | M | .github/workflows/deploy.yml L78-L85
42 | Feature | Implement admin/user role separation | Data/Control Plane | 1 | High | AI Agent | New | Single endpoint serves both admin operations (assessment config, report generation) and user queries. No role-based access control within the app. Any authenticated user can trigger background assessments. | Admin role required for /assessments POST, config changes, report deletion. User role for /chat, report viewing. Roles from Entra ID app roles. | L | api.py
43 | User Story | Add admin auth for assessment endpoints | Data/Control Plane | 2 | Medium | AI Agent | New | As a security engineer, /assessments POST endpoint only requires token presence, no admin role check. Any authenticated user can trigger resource-intensive background assessments. | Admin app role required for /assessments. Role check middleware. 403 for non-admin users. Audit log for all assessment triggers. | M | api.py L305-L310
44 | User Story | Fix path traversal risk in report serving | Data/Control Plane | 2 | Medium | AI Agent | New | As a security engineer, report serving uses pathlib.Path resolution but no explicit path-traversal check ensures the resolved path stays within _OUTPUT_DIR. | Explicit check: resolved_path.is_relative_to OUTPUT_DIR. Return 403 on traversal attempt. Log traversal attempts as security events. | S | api.py report serving
45 | User Story | Migrate in-memory task state to Redis/DB | Data/Control Plane | 3 | Low | AI Agent | New | As a platform engineer, _tasks dict used for assessment status. Comment says "swap for Redis/DB in production" but production uses in-memory. Task state lost on restart. | Assessment state in Redis or Cosmos DB. Survives restarts. Queryable status history. Multi-replica consistent. | M | api.py L301-L302
46 | User Story | Implement per-user token budget enforcement | Model Governance | 2 | Medium | AI Agent | New | As a platform engineer, token usage tracked but no per-user/per-session limit. Single user can exhaust 30K TPM model capacity affecting all users. | Per-user hourly token budget (configurable, default 10K). Per-assessment cap. 429 response when budget exceeded. Admin override capability. | M | api.py L580-L585
47 | User Story | Implement model drift detection | Model Governance | 2 | Medium | AI Agent | New | As a QA engineer, no comparison of model output quality over time. No regression tests against known-good outputs. Model version updates could silently degrade quality. | Weekly benchmark run against 50 golden test cases. Accuracy tracked over time. Alert on >5% quality degradation. Automated rollback trigger. | L | tests/
48 | User Story | Pin model version at runtime | Model Governance | 3 | Low | AI Agent | New | As a developer, deployment uses named model (e.g., "gpt-4.1") which Azure may auto-update. No control over which specific model version serves requests. | Model version pinned in config (e.g., gpt-4.1-2025-04-14). Version change requires explicit config update. Pre-upgrade benchmark required. | S | api.py L53
49 | User Story | Review fallback model cost implications | Model Governance | 3 | Low | AI Agent | New | As a platform owner, fallback model is gpt-5.1 (MORE capable/expensive than primary gpt-4.1). Frequent primary failures escalate costs. No cost tracking per model. | Cost tracking per model. Alert when fallback usage >10%. Evaluate if fallback should be same-tier or lower-tier model. Budget cap per model. | S | api.py L53-L54
50 | Feature | Move MSAL tokens from localStorage to sessionStorage | Cross-Cutting | 1 | Critical | Webapp | New | MSAL tokens stored in localStorage across all 9 HTML pages with cacheLocation:"localStorage". Tokens persist in plaintext DOM after browser close. Extractable via any XSS vulnerability. | All 9 pages: cacheLocation:sessionStorage. Tokens cleared on browser close. Combined with strict CSP to prevent XSS extraction. Verified via security scan. | M | webapp/*.html L816
51 | Feature | Implement Comprehensive Content Security Policy | Cross-Cutting | 1 | Critical | AI Agent | New | CSP only includes frame-ancestors. Missing: default-src, script-src, style-src, img-src, object-src, base-uri. Allows inline scripts and arbitrary resource loading. | Full CSP: default-src self; script-src self nonce-random; style-src self unsafe-inline; object-src none; base-uri self; form-action self. CSP report-uri configured. | M | api.py L253-L258
52 | User Story | Add missing security headers | Cross-Cutting | 1 | High | AI Agent | New | As a security engineer, missing: Strict-Transport-Security, X-Content-Type-Options, Referrer-Policy, Permissions-Policy. Only HSTS and nosniff prevent protocol downgrade and MIME sniffing. | HSTS: max-age=31536000; includeSubDomains. X-Content-Type-Options: nosniff. Referrer-Policy: strict-origin-when-cross-origin. Permissions-Policy: camera=(), microphone=(). | S | api.py L253
53 | User Story | Restrict CORS to exact origins | Cross-Cutting | 2 | Medium | AI Agent | New | As a security engineer, CORS allows wildcard Teams domains (https://*.teams.microsoft.com) with allow_credentials=True. Overly broad origin matching. | CORS restricted to exact known origins. No wildcard patterns with credentials. Origin allowlist managed in config. Audit CORS violations. | S | api.py L242-L248
54 | User Story | Implement SIEM export retry mechanism | Cross-Cutting | 2 | Medium | AI Agent | New | As an SRE, failed SIEM batches logged but silently dropped. No retry mechanism. Security events may be lost without detection. | Retry 3x with exponential backoff. Dead-letter blob for failed batches. Alert on >5% failure rate. Batch replay capability. | M | siem_integration.py L140-L150
55 | User Story | Fix SSRF via DNS rebinding in webhook validation | Cross-Cutting | 2 | Medium | AI Agent | New | As a security engineer, _validate_webhook_url checks IP at validation time but DNS can change at request time (DNS rebinding). No timeout on HTTP ops. | DNS pinning (resolve once, use IP). 5s connection timeout. 30s total timeout. 1MB response limit. Re-validate IP at request time. | M | api.py L282-L296
56 | User Story | Enable CMK encryption on storage account | Cross-Cutting | 2 | Medium | Infra | New | As a security engineer, storage account uses Standard_LRS with Microsoft-managed keys only. No customer-managed key encryption. | CMK via Key Vault. Key rotation every 90 days. RA-GRS for geo-redundancy. Encryption verified in compliance scan. | M | deploy.ps1 L225
57 | User Story | Implement SOC integration for AI alerts | Cross-Cutting | 2 | Medium | Infra | New | As an SRE, no Sentinel integration for AI-specific security alerts. No SOC routing for Defender for AI alerts. No correlation with SIEM events. | Sentinel workspace connected. Defender for AI alerts routed to SOC. Playbook for automated response. Weekly AI security review. | L | Infra

## Framework Summary
Security Framework | Alignment Score | Grade | Critical | High | Medium | Low | Total Items | Top Risk
AI-Specific Security | 20% | F | 1 | 3 | 1 | 0 | 5 | No prompt injection defense on user input
Zero Trust | 35% | D | 1 | 3 | 2 | 0 | 6 | JWT decoded without signature verification
Defender for AI | 0% | F | 0 | 2 | 2 | 0 | 4 | Defender for AI not enabled at all
OWASP LLM Top 10 | 40% | D | 2 | 3 | 4 | 1 | 10 | LLM01 Prompt Injection VULNERABLE
NIST AI RMF | 15% | F | 0 | 0 | 4 | 0 | 4 | No AI governance docs, no risk register
Responsible AI | 25% | F | 0 | 2 | 2 | 2 | 6 | No accountability trail, no GDPR erasure
Supply Chain | 50% | C | 0 | 1 | 3 | 2 | 6 | Beta/RC SDKs in production
Data/Control Plane | 30% | D | 0 | 1 | 2 | 1 | 4 | No admin/user role separation
Model Governance | 40% | D | 0 | 0 | 2 | 2 | 4 | No token budget enforcement
Cross-Cutting | 20% | F | 2 | 1 | 5 | 0 | 8 | MSAL tokens in localStorage (XSS risk)
OVERALL | ~25% | F | 6 | 16 | 27 | 8 | 57 | Platform assesses others for controls it lacks itself

## Priority Matrix
Priority | AI-Specific Security | Zero Trust | Defender for AI | OWASP LLM Top 10 | NIST AI RMF | Responsible AI | Supply Chain | Data/Control Plane | Model Governance | Cross-Cutting | TOTAL
P1 | 3 | 4 | 2 | 5 | 0 | 2 | 1 | 1 | 0 | 3 | 21
P2 | 2 | 1 | 2 | 5 | 4 | 2 | 3 | 2 | 2 | 5 | 28
P3 | 0 | 1 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 0 | 8
TOTAL | 5 | 6 | 4 | 10 | 4 | 6 | 6 | 4 | 4 | 8 | 57

## Top 15 Critical Gaps
Rank | Finding | Framework | Risk Level | File Reference | Sprint Target
1 | No prompt injection defense - user input passes directly to GPT | OWASP LLM01 / CAF Agent Security #5 | CRITICAL | api.py L357 | Sprint 1
2 | No Azure AI Content Safety / Prompt Shields | CAF Agent Security #5 / Content Safety | CRITICAL | Infra/app | Sprint 1
3 | Defender for AI not enabled | CAF Agent Security #2 | CRITICAL | deploy.ps1 | Sprint 1
4 | JWT tokens decoded without signature verification | Zero Trust / CAF #6 | CRITICAL | core/auth.py L62-75 | Sprint 1
5 | MSAL tokens in localStorage (XSS-extractable) | OWASP LLM06 / Zero Trust | CRITICAL | webapp/*.html | Sprint 1
6 | Incomplete CSP (only frame-ancestors) | OWASP / MS Security Benchmark | CRITICAL | api.py L253-258 | Sprint 1
7 | OAuth tokens in POST body - logged and in LLM context | Zero Trust / CAF #7 | HIGH | api.py L270-273 | Sprint 2
8 | No WAF on public Container App endpoint | Zero Trust / FedRAMP SC-7 | HIGH | deploy.ps1 L381 | Sprint 2
9 | No model output validation - streamed to client raw | OWASP LLM02 / Content Safety | HIGH | api.py L601-650 | Sprint 2
10 | No adversarial testing / red teaming | CAF Agent Security #4 / NIST AI RMF | HIGH | Tests | Sprint 2
11 | No agent registry for 9+ agent modes | CAF Governance #2 | HIGH | System design | Sprint 3
12 | No AI incident response plan | CAF Agent Security #10 / NIST MANAGE | HIGH | Documentation | Sprint 3
13 | No PII masking in logs or assessment evidence | GDPR / CAF Data Governance | HIGH | Evidence collectors | Sprint 2
14 | No GDPR right-to-erasure support | CAF Regulatory Compliance | HIGH | api.py | Sprint 3
15 | No Responsible AI Impact Assessment | CAF RAI / NIST AI RMF GOVERN | MEDIUM | Documentation | Sprint 4

## Sprint Roadmap
Sprint | Focus | Items | Critical | High | Goal
Sprint 1 (Immediate) | Critical Security Gaps | Items 1,6,50,51 + Defender enablement | 6 | 4 | Enable Defender for AI, integrate Prompt Shields, fix JWT validation, move MSAL to sessionStorage, implement full CSP
Sprint 2 | High-Risk Remediation | Items 2,3,8,10,17,20,23,52 | 0 | 8 | Add WAF via Front Door, move tokens to Auth header, implement I/O validation pipeline, enable Dependabot, mask PII
Sprint 3 | Governance & Compliance | Items 26,27,31,42,51 + GDPR | 0 | 5 | Build RAI governance framework, AI incident response plan, GDPR erasure, admin role separation, agent registry
Sprint 4-6 | Framework Maturity | Items 28,29,33,34,35,46,47 + ISO prep | 0 | 2 | NIST AI RMF lifecycle, accuracy benchmarks, fairness testing, model governance, ISO 42001 readiness, Purview integration