## RADS Compliance Backlog
ID | Work Item Type | Title | RADS Pillar | Priority | Risk Level | Area | State | Description | Acceptance Criteria | Effort
1 | Epic | RADS: Reliability Engineering | Reliability | 1 | High | Architecture | New | Ensure system functions correctly and consistently under expected/unexpected conditions with fault-tolerance and self-healing capabilities. | All reliability features implemented, tested, and documented. MTBF targets defined and met. | XL
2 | Feature | Implement Circuit Breaker Pattern | Reliability | 1 | High | AI Agent | New | Add circuit breaker for Azure API calls (ARM, Graph, OpenAI) to prevent cascading failures when downstream services degrade. Currently collectors retry indefinitely within 300s timeout with no trip-wire. | Circuit breaker trips after 5 consecutive failures per service endpoint. Half-open state tests recovery every 30s. Dashboard shows circuit state. | L
3 | Feature | Distributed Rate Limiting | Reliability | 1 | High | AI Agent | New | Replace in-memory _RateLimitMiddleware with Redis-backed distributed rate limiter. Current implementation breaks when Container App scales to multiple replicas. | Rate limits enforced consistently across all replicas. Redis failover does not block requests (degrade to local). Metrics exported to App Insights. | L
4 | User Story | Add global assessment timeout | Reliability | 2 | Medium | AI Agent | New | As a platform engineer, I need a global assessment timeout (beyond per-collector 300s) so that runaway assessments cannot consume resources indefinitely. | Global timeout configurable (default 30min). Partial results returned on timeout. User notified with progress percentage. | M
5 | User Story | Migrate from beta/RC Agent Framework SDKs | Reliability | 2 | High | AI Agent | New | As a developer, I need to track GA release of agent-framework-azure-ai (currently 1.0.0rc3) and azure-ai-agentserver-agentframework (1.0.0b16) to avoid breaking API changes. | Migration plan documented. Automated test validates SDK upgrade path. Pinned to GA version when available. | M
6 | User Story | Implement automated dependency scanning | Reliability | 1 | High | DevOps | New | As a security engineer, I need Dependabot or OWASP Dependency-Check in CI to detect vulnerable transitive dependencies. Currently only top-level packages are pinned. | GitHub Dependabot enabled. Weekly scan runs. Critical CVEs auto-create PRs. SBOM generated per release. | M
7 | User Story | Add end-to-end integration tests | Reliability | 2 | Medium | AI Agent | New | As a QA engineer, I need E2E tests covering full assessment workflows (PostureIQ, RBAC, Risk, Data Security) against mock Azure endpoints. Only 5 test files exist. | E2E tests cover all 9 assessment types. Mock ARM/Graph endpoints. Tests run in CI pipeline. >80% code path coverage. | XL
8 | User Story | Implement retry with jitter for OpenAI calls | Reliability | 3 | Medium | AI Agent | New | As a developer, I need exponential backoff with jitter for Azure OpenAI rate limit errors to avoid thundering herd when multiple assessments hit TPM limits simultaneously. | Retry uses exponential backoff (1s, 2s, 4s, 8s) with random jitter (0-1s). Max 4 retries before fallback model. | S
9 | Epic | RADS: Availability Engineering | Availability | 1 | High | Architecture | New | Ensure system is accessible and operational during promised time periods with defined SLA/SLO targets and minimal downtime during deployments. | SLA/SLO published. Blue-green deployment active. Uptime monitoring with alerting. <5min deployment downtime. | XL
10 | Feature | Blue-Green Deployment Strategy | Availability | 1 | High | Infra | New | Implement blue-green deployment for Container App revisions to enable zero-downtime deployments and instant rollback. Currently single-revision updates. | Traffic split supports 0/100 and gradual rollout. Rollback completes in <60s. Health check gates promotion. | L
11 | Feature | Define and Publish SLA/SLO/SLI | Availability | 1 | Medium | Architecture | New | Define Service Level Agreements, Objectives, and Indicators. No SLA/SLO/RTO/RPO targets currently documented. | SLA: 99.5% monthly uptime. SLO: assessment <15min. SLI: health check <200ms. RTO: 30min. RPO: 24h. | M
12 | User Story | Implement automated post-deployment smoke tests | Availability | 2 | Medium | DevOps | New | As a DevOps engineer, I need automated smoke tests after each deployment to validate /health, /chat, and auth endpoints before promoting the revision. | Smoke test script runs post-deploy. Tests health, auth, basic chat. Blocks promotion on failure. | M
13 | User Story | Add semantic versioning and auto-increment | Availability | 3 | Low | DevOps | New | As a release manager, I need semver (MAJOR.MINOR.PATCH) instead of manual v95/v96 tags to track breaking changes and enable automated release notes. | Version follows semver. CHANGELOG auto-generated. Git tags on deploy. Image tagged with semver + git SHA. | M
14 | User Story | Implement uptime monitoring and alerting | Availability | 2 | Medium | Infra | New | As an SRE, I need external uptime monitoring with alerting when health endpoint fails for >2 consecutive checks. | Availability test configured. Alert on 2 consecutive failures. Teams notification. Monthly uptime report. | S
15 | User Story | Document multi-region disaster recovery plan | Availability | 3 | Medium | Infra | New | As an architect, I need a documented DR strategy for multi-region failover if North Europe becomes unavailable. Currently single-region. | DR plan with paired region. ACR geo-replication. Failover runbook tested quarterly. | L
16 | User Story | Add Container App autoscale rules | Availability | 2 | Medium | Infra | New | As a platform engineer, I need autoscale rules (min/max replicas, CPU/memory triggers, HTTP concurrent requests) for the Container App. | Autoscale: min 1, max 5 replicas. Scale on CPU >70% or requests >50. Cool-down 60s. Load tested. | S
17 | User Story | Implement load testing framework | Availability | 2 | Medium | DevOps | New | As a performance engineer, I need load tests simulating 50 concurrent users to identify bottlenecks and validate autoscale. | Azure Load Testing configured. 50 users, 15min. P95 <5s. Errors <1%. Results tracked per release. | L
18 | User Story | Add OpenAI token usage tracking and budgets | Availability | 2 | Medium | AI Agent | New | As a platform owner, I need per-assessment token usage tracked and budget alerts when approaching 30K TPM limit. | Token usage logged per assessment. Daily rollup in App Insights. Alert at 80% TPM. Cost attribution per tenant. | M
19 | User Story | Implement assessment queue for concurrent requests | Availability | 2 | Medium | AI Agent | New | As a platform engineer, I need an assessment queue to serialize heavy assessments and prevent resource contention. | Queue serializes beyond concurrency limit (3). Users see position. Priority queue. 30min timeout. | L
20 | Epic | RADS: Durability Engineering | Durability | 1 | High | Architecture | New | Ensure assessment data, reports, and audit logs are persistently stored, protected against loss/corruption, and recoverable within defined RPO targets. | All reports persisted durably. Audit trail complete. Backup and recovery tested. Data classified and encrypted. | XL
21 | Feature | Fix Persistent Storage for Reports | Durability | 1 | Critical | Infra | New | Resolve Azure Files volume mount failure (VolumeMountFailure/Permission denied). Reports save to ephemeral /agent/output and are lost on restart. Root cause: allowSharedKeyAccess=false policy. | Reports persist across restarts. Options: Managed Identity mount, Blob SDK upload, or Azure Files RBAC. | L
22 | Feature | Implement Audit Logging | Durability | 1 | High | AI Agent | New | Add comprehensive audit trail: who ran which assessment, what scope, when, what results. Currently no accountability tracking (only technical logs). | Audit log: user identity, timestamp, assessment type, scope, duration, finding count. Queryable in Log Analytics. | L
23 | User Story | Implement report archival to Blob Storage | Durability | 2 | Medium | AI Agent | New | As a compliance officer, I need all reports (HTML, PDF, Excel, SARIF) uploaded to Blob Storage with lifecycle policy. Currently local filesystem only. | Auto-upload post-generation. 90-day hot, 1-year cool, 7-year archive. Immutable for regulatory reports. | L
24 | User Story | Add data backup and recovery strategy | Durability | 2 | Medium | Infra | New | As an SRE, I need documented backup strategy for evidence, config, and historical reports with tested recovery procedures. | Daily backup. Recovery tested quarterly. RPO <24h verified. Backup integrity checks automated. | M
25 | User Story | Implement field-level encryption for sensitive findings | Durability | 3 | Medium | AI Agent | New | As a security engineer, I need sensitive findings (credential exposure, privilege escalation chains) encrypted at field level before storage. | Sensitive fields encrypted with Key Vault CMK. Decryption requires explicit RBAC role. | L
26 | Bug | SIEM export has no retry mechanism | Durability | 2 | Medium | AI Agent | New | SIEM export (Sentinel/Splunk) has no retry on failure. Failed batches silently dropped with only a log entry. | Retried 3x with backoff. Dead-letter blob for failed batches. Alert on >5% failure rate. | M
27 | User Story | Enable blob encryption with CMK | Durability | 1 | High | Infra | New | As a security engineer, I need storage account encrypted with customer-managed keys (CMK) instead of Microsoft-managed keys. Currently Standard_LRS without CMK. | CMK enabled via Key Vault. RA-GRS for geo-redundancy. Encryption verified in compliance reports. | M
28 | Epic | RADS: Security Engineering | Security | 1 | Critical | Architecture | New | Protect the system from attacks by maintaining confidentiality, integrity, and availability. Address OWASP Top 10, Zero Trust, and defense-in-depth across all components. | All critical/high security findings remediated. Pen test passed. WAF active. Secrets in Key Vault. CSP enforced. | XL
29 | Feature | Secure Token Handling Architecture | Security | 1 | Critical | AI Agent | New | OAuth tokens (graph_token, arm_token) passed in POST body to /chat are logged at DEBUG, stored in memory history, decoded without signature verification, and never cleared post-request. High risk of token exposure. | Tokens passed via Authorization header only. Token scrubbing in all log pipelines. Memory cleared post-request. JWT signature validated. | L
30 | User Story | Fix token expiry silent failure | Security | 1 | High | AI Agent | New | As a user, UserTokenCredential only warns if token expires in <120s but does not raise exception. Requests fail silently with 401 downstream. No forced re-auth mechanism. | Exception raised on near-expiry. Auto token refresh before expiry. 401 returns clear re-authenticate message to client. | M
31 | User Story | Move localStorage to sessionStorage for MSAL tokens | Security | 1 | High | Webapp | New | As a security engineer, MSAL cacheLocation is localStorage across all 9 HTML pages. Tokens persist in plaintext DOM, extractable via XSS. sessionStorage clears on browser close. | All 9 pages use sessionStorage. Auto-clear on logout. CSP prevents inline script injection. PKCE flow enforced. | M
32 | User Story | Secure service principal credentials via Key Vault | Security | 1 | High | Infra | New | As a security engineer, AZURE_CLIENT_SECRET read from plaintext env var. deploy.ps1/setup.ps1 may expose secrets in command history. No rotation schedule. | All SP credentials stored in Key Vault. Retrieved via managed identity at startup. 90-day rotation enforced. No plaintext env vars. | M
33 | Feature | Comprehensive Input Validation Framework | Security | 1 | Critical | AI Agent | New | Multiple input validation gaps: domains param not validated, output_formats allowlist not enforced, no length limits on message field, framework list passed to LLM unvalidated. Webhook URL validation incomplete (DNS rebinding possible). | All inputs validated against strict allowlists. Max length constraints. Pydantic strict mode. DNS pinning for webhooks. Request size limits. | L
34 | Bug | Fix XSS risk in HTML report generation | Security | 1 | High | AI Agent | New | Resource names from Azure rendered in Jinja2 HTML reports. Custom esc() function in shared_theme.py not used consistently. Some evaluator fields (control_title, description) passed unescaped. | Jinja2 autoescape=True globally. Replace custom esc() with markupsafe.escape. Unit test with XSS payloads across all report templates. | S
35 | Bug | Fix CSV injection risk in Excel export | Security | 1 | High | AI Agent | New | Excel/CSV exports do not escape special characters (=, +, -, @). Malicious Azure resource names could execute formulas when opened in Excel/Splunk. | All cell values stripped of formula chars or prefixed with single-quote. Test with injection payloads passes. | S
36 | User Story | Fix SSRF risk in webhook delivery | Security | 1 | High | AI Agent | New | As a security engineer, _validate_webhook_url() rejects private IPs but DNS rebinding bypasses validation. No timeout on HTTP ops. No request body size limits. Webhook token in plaintext. | DNS pinning (resolve once). 5s timeout. 1MB body limit. HMAC-SHA256 signing. No sensitive data in webhook body. | M
37 | Feature | Implement Strict CSP and Security Headers | Security | 1 | High | AI Agent | New | CSP only includes frame-ancestors. Missing: default-src, script-src, style-src, img-src, object-src, base-uri. No X-Content-Type-Options, no X-XSS-Protection header. CORS allows wildcard Teams domains with allow_credentials=True. | Full CSP: default-src self; script-src self; style-src self unsafe-inline; object-src none; base-uri self. X-Content-Type-Options: nosniff. CORS restricted to exact origins. | M
38 | User Story | Move SIEM auth tokens to Key Vault | Security | 1 | High | Security | New | As a security engineer, SIEM endpoint auth tokens (Sentinel DCR, Splunk HEC) held in SIEMConfig object in memory (plaintext). No rotation without redeployment. | All SIEM tokens in ESIQNew-kv. Retrieved via managed identity. Rotation without redeployment. Audit access logged. | M
39 | User Story | Scope managed identity to least privilege | Security | 1 | High | Infra | New | As a security engineer, ESIQNew-identity has Contributor role on subscription. Should be scoped to Cognitive Services User, Storage Blob Data Contributor, Key Vault Secrets User, Reader. | Contributor removed. Scoped roles: Cognitive Services User, Blob Contributor, KV Secrets User, Reader. Verified with check_permissions tool. | S
40 | User Story | Remove secrets from deployment script history | Security | 2 | High | Infra | New | As a DevOps engineer, deploy.ps1/setup.ps1 expose tenant IDs, subscription IDs, custom domains in plaintext. Generated .generated/runtime.json unencrypted. | Sensitive output stored in Key Vault. PowerShell history sanitized. runtime.json encrypted or stored in KV. Secrets masked in logs. | M
41 | Feature | Security Testing & Pen Test Suite | Security | 1 | High | Security | New | No security tests exist. No OWASP ZAP scan, no input fuzzing, no auth bypass tests, no CSV/XSS injection tests, no SSRF tests, no penetration testing. | OWASP ZAP in CI. Input fuzzing for /chat. Auth bypass tests. Injection tests. Pen test report quarterly. All critical findings remediated. | L
42 | User Story | Enable container image vulnerability scanning | Security | 2 | High | DevOps | New | As a security engineer, no ACR image scanning configured. No Microsoft Defender for Containers. Vulnerabilities in base image or pip packages undetected. | Defender for Containers on ACR. Critical vulns block deploy. Weekly scans. Remediation SLA: Critical=24h, High=7d. | M
43 | User Story | Add WAF to Container App ingress | Security | 2 | High | Infra | New | As a security engineer, Container App has no Web Application Firewall. No OWASP rule set protection. Direct public endpoint without L7 filtering (FedRAMP SC-7 gap). | Azure Front Door with WAF deployed. OWASP 3.2 rule set enabled. Rate limiting at edge. DDoS protection. Bot detection. | L
44 | User Story | Implement PII masking in logs | Security | 2 | Medium | AI Agent | New | As a compliance officer, user names, emails, resource IDs logged as-is. No PII masking. No sensitive field redaction configured in logger. | PII fields hashed with SHA-256. Regex-based secret redaction (tokens, keys, connection strings). No PII in App Insights. | M
45 | User Story | Add structured security event logging | Security | 2 | Medium | AI Agent | New | As an SRE, no structured logging of: auth failures, token validation failures, rate limit hits, access denied events, config changes. Error logs may contain partial tokens. | All auth events logged: success/failure/refresh/scope warnings. Token values never logged. Security events in dedicated category. | M
46 | User Story | Implement FedRAMP/NIST 800-53 control mappings | Security | 2 | High | Security | New | As a compliance officer, missing controls: SC-7 (Boundary Protection/no WAF), AU-2 (Audit Events), AC-2 (Account Mgmt), SC-13 (FIPS 140-2), SI-4 (IDS/IPS). | Control mapping document. WAF (SC-7). Audit logging (AU-2). FIPS crypto validation (SC-13). Defender integration (SI-4). | L
47 | Epic | RADS: Data Protection & Governance | Data Governance | 1 | High | Architecture | New | Establish data protection, classification, retention, lineage, and privacy controls across all assessment data, reports, and user information. | Data classified and labeled. Retention enforced. GDPR compliance. Lineage tracked. Quality validated. Consent managed. | XL
48 | Feature | Implement Data Retention Policy | Data Governance | 1 | High | AI Agent | New | Assessment results stored indefinitely in blob storage. No automatic cleanup or archival. History keeps last 500 entries without rotation. No distinction between operational and archival data. | Retention tiers: Hot 30d, Warm 90d, Cold 2yr. Auto-delete after retention. Policy enforced via Azure lifecycle management. Audit compliance. | L
49 | Feature | Implement Data Classification & Labeling | Data Governance | 1 | High | AI Agent | New | Reports exported without classification labels. No distinction between public summary vs sensitive findings. No PII handling in evidence. No sensitivity metadata tracked. | Findings classified: Public/Internal/Confidential/Restricted. Labels in report headers and metadata. Field-level masking based on classification. | L
50 | User Story | Mask sensitive data in assessment evidence | Data Governance | 1 | High | AI Agent | New | As a compliance officer, evidence records may contain passwords, API keys, connection strings found during assessment. No sanitization before storage. Reports exported as-is without redaction. | Data sanitization layer before storage. Mask: connection strings, API keys, passwords, PII. Sensitive findings tagged and excluded from default exports. | L
51 | Feature | GDPR Right-to-Erasure Support | Data Governance | 1 | High | AI Agent | New | No API to delete user historical data. Cannot respond to GDPR data subject requests (45-day requirement). Evidence contains PII (emails, names) stored indefinitely. No purge capability. | DELETE /api/user-data/{userId} endpoint. Purge hold period for GDPR. Cascading delete across blob + history. DPIA documented. | L
52 | User Story | Implement consent management for data collection | Data Governance | 2 | Medium | AI Agent | New | As a compliance officer, no consent recorded for data collection from Azure/Entra. No opt-in for multi-tenant scanning. Users unaware assessments collect PII (risky users, guest accounts). | Explicit opt-in before assessment. Consent recorded with timestamp/scope. Privacy notice displayed. Consent withdrawal mechanism. | M
53 | User Story | Implement multi-tenant data isolation | Data Governance | 1 | High | AI Agent | New | As a security engineer, tenant_id used in blob naming but no access control enforcement. Theoretical cross-tenant history access if blob name guessed. No per-tenant container isolation. | Per-tenant blob containers. RBAC: only tenant admins access their data. Cryptographic isolation. Audit cross-tenant access attempts. | L
54 | User Story | Implement data lineage tracking | Data Governance | 2 | Medium | AI Agent | New | As a compliance officer, evidence collected but origin/source not tracked. Cannot trace: evidence -> findings -> recommendation -> action. No audit trail of data transformations. | Track: collector -> evidence -> evaluator -> finding -> report. Metadata: source API, query, scope, timestamp, user. Change tracking. | M
55 | User Story | Add data quality controls for evidence | Data Governance | 2 | Medium | AI Agent | New | As a QA engineer, no validation of evidence before evaluation. Missing data not flagged. Incomplete collection (403 errors) marked as successful. No completeness metrics. | Evidence validation before eval. Completeness tracking per resource type. Partial findings flagged. Confidence score in reports. | M
56 | User Story | Add data classification labels to all report exports | Data Governance | 3 | Low | AI Agent | New | As a compliance officer, reports need classification labels (Confidential, Internal, Public) based on finding severity. Purview integration optional. | Auto-classified: Critical/High=Confidential, Medium=Internal, Low/Info=Public. Label in header/metadata/PDF watermark. | S
57 | User Story | Validate config against schema at startup | Data Governance | 3 | Low | AI Agent | New | As a developer, config loaded from ENTERPRISESECURITYIQ_CONFIG env var without schema validation. Arbitrary config injection if env var compromised. No integrity checks. | Config validated against config.schema.json at startup. Config signing (HMAC-SHA256). Audit config changes. | S
58 | User Story | Enforce TLS 1.3 for SIEM export connections | Data Governance | 2 | Medium | AI Agent | New | As a security engineer, SIEM export code does not enforce TLS 1.2+ explicitly. No certificate pinning. Auth tokens in Authorization header without certificate validation. | TLS 1.3 minimum for SIEM connections. Certificate pinning for known endpoints. Request signing with timestamps. | M

## RADS Summary
RADS Pillar | Current State | Target State | Epics | Features | Stories/Bugs | Critical Items | Key Risk
Reliability | Moderate (60%) | 95% | 1 | 2 | 5 | 2 | No circuit breaker; beta SDKs; no E2E tests
Availability | Moderate (55%) | 99.5% SLA | 1 | 2 | 8 | 1 | No blue-green; no SLA defined; no load testing
Durability | Low (40%) | 95% | 1 | 2 | 4 | 2 | Ephemeral storage; no audit trail; no CMK encryption
Security | Low (30%) | 95% | 1 | 4 | 10 | 5 | Token exposure in POST body; XSS/CSV injection; no WAF; no CSP; overpermissive RBAC
Data Governance | Very Low (20%) | 90% | 1 | 3 | 8 | 3 | No retention policy; no GDPR erasure; no data classification; no tenant isolation; PII in evidence

## Priority Matrix
Priority | Reliability | Availability | Durability | Security | Data Governance | TOTAL
P1 | 4 | 3 | 4 | 13 | 6 | 30
P2 | 3 | 6 | 3 | 6 | 4 | 22
P3 | 1 | 2 | 1 | 0 | 2 | 6
TOTAL | 8 | 11 | 8 | 19 | 12 | 58